## Sheet1
Story ID | Story Name | Description (As a / I want / So that) | Priority | Iteration (Sprint) Number | Acceptance Criteria | Estimation (Man-days) | Technical Notes & Dependencies | Planned Start Date | Completion Date
TA001 | System User Role Registration & Login | As a applicant/recruiter/admin | Critical | Sprint 01 | 1. Role selection for registration: Applicant/Recruiter/System Admin (three independent role types, no cross-switching by default) | 7 | 1. Design role-based data table (user_base + applicant/recruiter/admin sub-tables) | 2026-03-19 | 2026-XX-XX
|  | I want to register an account by role and log in with account + password (SMS verification optional) |  |  | 2. Applicant registration: verify student ID/school email (edu domain); fill in basic info (name, major, grade, phone) |  | 2. Add school email/student ID verification interface
|  | So that I can access the system functions matching my role and start TA recruitment-related operations |  |  | 3. Recruiter registration: verify teacher ID/school department approval code; bind to a specific college/course
4. Admin registration: only open to system super administrators (manual account creation by technical team, no self-registration)
5. Login: support account+password; "forgot password" via bound phone/email; auto-login for 7 days on trusted devices
6. Login success jumps to role-specific home page; permission verification for all subsequent page access
TA002 | TA Recruitment Position Release (Recruiter End) | As a course recruiter/college teacher | Critical | Sprint 01 | 1. Position release form includes: course name, college, TA type (full-time/part-time), recruitment quota, application requirements (major, grade, GPA, skills), job content, interview time/location, deadline | 6 | 1. Support attachment upload (PDF/Word, max 5MB); | 2026-03-20 | 2026-XX-XX
|  | I want to release TA recruitment positions, edit/delete unpublished positions, and put published positions online/offline |  |  | 2. Support rich text editing for job content (insert bullet points, links, attachment uploads like job description documents) |  | 2. Public list supports fuzzy search (course name/college) for applicants
|  | So that I can publish recruitment requirements for my courses/colleges and attract eligible applicants |  |  | 3. Unpublished positions: editable/deletable; published positions: online/offline toggle (offline positions not visible to applicants)
4. System verifies mandatory fields (course name, quota, deadline) – no submission without completion
5. Released positions display in the public recruitment list (applicant end) with sorting by release time/deadline
TA003 | TA Position Application & Resume Submission (Applicant End) | As a applicant | Critical | Sprint 02 | 1. Position browsing: filter by college/major/course name/quota; sort by release time/deadline; view detailed position info (including attachment preview) | 6 | 1. Add application data table (bind applicant ID + position ID + application status) | 2026-03-27 | 2026-XX-XX
|  | I want to browse public TA positions, apply for eligible positions, and submit a personalized resume (basic info + TA-related experience) |  |  | 2. Application eligibility check: system auto-matches position requirements (e.g., grade/major) – prompt "ineligible" if not matched |  | 2. Set application limit logic (count submitted applications for each applicant ID)
|  | So that I can compete for TA positions that match my major/ability and deliver my qualification to recruiters |  |  | 3. One applicant can apply for max 3 positions (system limit to avoid duplicate review); display application status (pending review/under review/rejected/admitted) for each application |  | 3. Attachment preview supports online PDF/Word viewing (no download by default)
4. Resume submission: built-in resume template (auto-fill registered basic info); editable fields (GPA, professional skills, TA/teaching experience, self-introduction); support resume export as PDF
5. Application submission: confirm with one-click; no modification after submission (only withdrawal before recruiter review)
TA004 | Application Review & Score Management (Recruiter End) | As a TA recruiter | High | Sprint 02 | 1. Review list: filter by application status/position name; display applicant basic info + resume preview + application time | 6 | 1. Design scoring data table (bind recruiter ID + applicant ID + position ID + dimension scores + total score) | 2026-03-29 | 2026-XX-XX
|  | I want to view all applications for my released positions, review applicant resumes, score applicants (quantitative), and mark review results |  |  | 2. Scoring system: customizable score dimensions (GPA: 0-30, skills:0-20, experience:0-30, self-introduction:0-20; total 100 points) |  | 2. Add comment input box (20-500 characters); mandatory verification for non-advance results
|  | So that I can screen eligible applicants efficiently and select candidates for the interview round |  |  | 3. Review results: mark as Reject/Advance to Interview/Reserve; add review comments (mandatory for reject/reserve) |  | 3. Real-time score calculation and ranking (front-end + back-end double verification)
4. Batch operation: support batch reject/advance for multiple applicants (improve review efficiency)
5. Score ranking: auto-sort applicants by total score for each position; display ranking in the review list
TA005 | Interview Notice Sending & Confirmation (Dual End) | As a recruiter/applicant | High | Sprint 03 | 1. Recruiter end: select shortlisted applicants → fill in interview info (time, location, online/offline, contact person) → one-click send notice (system push + SMS/email reminder optional) | 5 | 1. Integrate SMS/email notification API (optional, for key reminders); add notification switch for applicants | 2026-04-07 | 2026-XX-XX
|  | Recruiter: I want to send interview notices to shortlisted applicants (set time/location/format) |  |  | 2. Applicant end: notice pop-up on home page; detail page shows interview info + "Accept/Decline" button; record confirmation result in the system |  | 2. Develop Excel export function for attendance list (with filter by confirmation status)
|  | Applicant: I want to receive interview notices in the system and confirm attendance (accept/decline) |  |  | 3. Recruiter end: view interview attendance list (sorted by accept/decline/pending); export list as Excel |  | 3. Add interview notice data table (bind position ID + applicant ID + interview info + attendance status)
|  | So that recruiters can arrange interviews efficiently and applicants can confirm participation in a timely manner |  |  | 4. Auto-reminder: system sends SMS/email reminder to applicants 24 hours before the interview
5. Interview notice editing: recruiter can modify interview info and resend notice before the deadline
TA006 | Interview Result Entry & Final Admission Release (Recruiter End) | As a TA recruiter | High | Sprint 03 | 1. Interview result entry: bind to applicant ID; fill in interview score (0-100) + comprehensive evaluation + final result (Admit/Reject) | 5 | 1. Add comprehensive score calculation logic (configurable weight for resume/interview scores) | 2026-04-08 | 2026-XX-XX
|  | I want to enter interview scores/results for applicants and release the final admission list for each TA position |  |  | 2. Final admission list: auto-generate for each position (sorted by comprehensive score = resume score60% + interview score40%); support manual adjustment (for special cases) |  | 2. Admission list page supports fuzzy search (applicant name/student ID) for recruiters
|  | So that I can confirm the final TA hires and notify successful applicants in a standardized way |  |  | 3. Result release: one-click publish admission list (visible to all applicants; only show "admitted/rejected" for each applicant, hide others' scores) |  | 3. Hide other applicants' data for applicants (data isolation by role permission)
4. Admission notice: system auto-send to admitted applicants (system push + SMS/email); include TA onboarding info (training time, contact person)
5. Result record: all interview/admission data is stored permanently for future query/audit
TA007 | Personal Application/Review Record Query (Dual End) | As a applicant/recruiter | Medium | Sprint 04 | 1. Applicant end: record list sorted by application time; display position name, application status, review comments (if any), interview/ admission result; support filter by status/position | 6 | 1. Add data statistics component (recruiter end) for real-time count of key indicators | 2026-04-18 | 2026-XX-XX
|  | Applicant: I want to view all my TA applications, review status, interview results, and admission records |  |  | 2. Recruiter end: position list + application/review/interview/admission data for each position; support data statistics (total applications/shortlisted/admitted numbers) |  | 2. Develop PDF/Excel export templates for different roles (customized fields)
|  | Recruiter: I want to view all my released positions, application data, review records, and final admission lists |  |  | 3. All records support detail view; historical records (≥1 semester) are archived but still queryable
|  | So that both sides can track the entire recruitment process and check historical records at any time |  |  | 4. Export function: applicant can export personal application records as PDF; recruiter can export all recruitment data of their positions as Excel
TA008 | System Data Statistics & Visualization (Admin End) | As a system administrator | Medium | Sprint 04 | 1. Statistics cards: total released positions, total applicants, total admitted TAs, average application per position, college recruitment completion rate | 5 |  | 2026-04-20 | 2026-XX-XX
|  | I want to view the overall TA recruitment data of the school/college with charts and statistics cards, and filter by time/college/course |  |  | 2. Visual charts: bar chart (recruitment volume by college), line chart (application trend by time), pie chart (TA type distribution: full-time/part-time)
|  | So that I can grasp the overall recruitment situation and make data-driven management decisions |  |  | 3. Data filter: by academic semester/college/course type; support custom time range
4. Data refresh: real-time refresh (latency ≤5s); chart supports hover to view detailed data
5. Data export: one-click export of overall recruitment statistics as Excel/PDF for administrative reporting
TA009 | System Permission Management & Account Maintenance (Admin End) | As a system administrator | Low | Sprint 04 | 1. Recruiter account review: verify new recruiter registrations; approve/reject with comments; bind to college/course after approval | 6 | 1. Add back-end permission interceptor to prevent unauthorized API access | 2026-05-08 | 2026-XX-XX
|  | I want to manage user roles/permissions, review recruiter accounts, freeze invalid accounts, and modify system basic settings |  |  | 2. Permission management: fine-grained control (module: position release/review/interview/result; operation: view/add/edit/delete) |  | 2. Design system operation log table (record admin ID/operation type/time/IP) for security audit
|  | So that I can ensure system security and standardize user access and operation |  |  | 3. Account maintenance: freeze invalid accounts (applicant/recruiter); reset user passwords; view all user login logs
4. System settings: modify application limit (max positions per applicant), score weight (resume/interview), notification rules (SMS/email)
5. Operation logs: record all admin operations (account review/permission modification) for audit
TA010 | System Optimization & Exception Handling (Technical End) | As a backend/front-end developer | Low | Sprint 04 | 1. Performance optimization: page load time ≤2s; optimize database index (key fields: applicant ID/position ID/ application status); reduce API request frequency | 5 | 1. Use front-end anti-shake/throttle to prevent duplicate submission; add XSS filter for input fields | 2026-05-08 | 2026-XX-XX
|  | I want to optimize system performance, fix known bugs, and add exception handling for key operations |  |  | 2. Exception handling: add prompt for network failure/operation timeout; handle duplicate submission (e.g., double-click application); prevent SQL injection/XSS attacks |  | 2. Optimize database index for frequently queried tables (application/position/review)
|  | So that I can improve system stability, reduce page load time, and avoid abnormal user operations |  |  | 3. Bug fix: repair known issues (e.g., resume export format error, score calculation error) |  | 3. Configure automatic database backup (MySQL/MariaDB) and set backup file storage path
[5 empty] | 4. Responsive adaptation: optimize page display for PC/tablet (no layout disorder); support basic operation on mobile devices |  | 4. Do cross-browser testing (Chrome/Firefox/Edge) to ensure compatibility
5. System backup: auto-backup database daily (at 00:00); backup files retained for 30 days for disaster recovery